## Sheet1
BugTracker Sprint 1
Tasks to complete | Priority | Deadline | completed
Create repo | 1 | 2020-07-14 | 2020-07-14
DBMS v1 | 1 | 2020-07-14 | 2020-07-14
UI prototypes | 1 | 2020-07-14
mainscreen UI v1 | 2 | 2020-07-15
setup DB | 2 | 2020-07-15
new/edit UI v1 | 3
notifications UI v1 | 3